## Sheet1
BUG REPORT-FoodPanda
QA Team |  | REPORTED BY | Tasnia Sultana Hema | ENVIRONMENT | OS: Windows 10 , Browser: Chrome |  |  | ASSIGNED TO | Binu | DEV Team
BUG ID | BUG TITLE | STEPS TO REPRODUCE | EXPECTED RESULT | ACTUAL RESULT | SCREENSHOT/VIDEO | SEVERITY | PRIORITY | STATUS | DATE REPORTED | DEFECT PRIORITY | STATUS | DATE OF FIX | Comment
BUG_FP_login_01 | The cursor does not appear in the email field by default | 1. Go to https://www.foodpanda.com.bd/ 2. Click the "login" link | After clicking on the "login" link ,the cursor automatically focuses on the email field by default. | After clicking on the "Login" link, the cursor does not go to on the email field by default. | https://prnt.sc/iupVqTgWLbWl | Minor | low | NEW | 2025-01-29
BUG_FP_NAVBAR_02 | A relevent page does not display when clicking the cart icon | 1.click on the "cart icon" in the navbar | Clicking the cart icon redirects the user to the cart page or displays a dropdown with cart details | 404 Ooops! | https://prnt.sc/mRTsw7CaWklG | Critical | High | NEW | 2025-01-29
BUG_FP_Header_sec_03 | When click "Locate Me " button it doen't Suggest me my Location | 2. Locate the "Locate Me" Button 3. click on the "Locate Me" Button 4. observe the behavior 5. select location 6.click confirm location | The map should open ,and display the user's location with a confirmation option | Suggests Another Location automatically | https://prnt.sc/i5BLXcdG_3GE | Blocker | High | NEW | 2025-01-29
BUG_FP_Header_sec_04 | When click "Locate Me " button it Suggests nearest Location except my location (Edge browser) | 2. Locate the "Locate Me" Button 3. click on the "Locate Me" Button 4. observe the behavior 5. select location 6.click confirm location | This system should suggest a location automatically based on the user's current GPS Coordinates. | Suggests the nearest location | https://prnt.sc/JtooGyfjJfh3 | Blocker | High | NEW | 2025-01-29
BUG_FP_Header_sec_5 | Automatically selects the nearest location without notifying the user. | 1. leave the location input field empty 2. Click the "Find Food" Button 3. Observe the system's behavior | This system should prompt the user to select or confirm a location manually ( a notification pr popup) | However, this system automatically selects the nearest location without notifying the user. | https://prnt.sc/Fl9uMXKONpjW | Critical | High | NEW | 2025-01-29
BUG_FP_Header_sec_06 | "Locate Me" and "Find Food" buttons are not keyboard accessible | 1. Use the "Tab" key to navigate through the header section . 2.Ensure both are "Locate Me" and "Find Food " buttons are Focuasable 3. Use " Tab" activate the buttons | Both Buttons should be navigable using the keyboard | Both Button is not working when using keyboard | https://prnt.sc/T3HKE7uYwI5u | Minor | low | NEW | 2025-01-29
BUG_DB_Pandamart_pg_7 | when selecting English to Bangla, it affects only the cart section. But it doesn't affect the whole page | 1. click the promotional banner 2. change the website language to another supported language | The banner content should be translated correctly into the selected language | just change cart option | https://prnt.sc/TywCQ3p8WX6C | Critical | Medium | NEW | 2025-01-29
BUG_Footer_08 | Invalid Credentials Do Not Trigger an Error Message | 1. Locate the Facebook icon 2. On the Facebook login page, enter invalid credentials (empty) 3. Click the login button | No error message should appear | appear error message(, "Email/phone and password are required.") | https://prnt.sc/vU0XloQac5H2 | Critical | High | NEW | 2025-01-29
BUG_Footer_09 | instagram login button is not working | 1. Open the FoodPanda website 2. Scroll to the footer 3. Observe the Instagram icon | The user should be logged in | The user should not be logged in (login button is not working ) | https://prnt.sc/kD01TyGg9ZRx | Critical | High | NEW | 2025-01-29